## Lab Brief
Lab 11 — Plan and Track a Release with GitHub Projects
Git and Github Masterclass · C171 · Version v2.2
Exam domain | Manage Projects with GitHub (5–10%)
Objective | Coordinate scope, ownership, timing and progress for a release.
Scenario | The CourseTrack Pro team needs one view of features, defects and release readiness.
Deliverable | A GitHub Project with table, board and roadmap views plus fields, workflows and insights
Tools | GitHub Projects, issues, milestones, labels, saved replies, Excel workbook
Workbook status | Completed sample — replace sample evidence with your own

## Evidence Log
Evidence Log
Record what you did, the result, and where the evidence can be verified.
Step | Action / decision | Expected evidence | Actual result | URL / screenshot ref | Status | Reviewer notes | Timestamp
1 | Create a project named CourseTrack Pro Release 1.1. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-01 | Complete | Meets acceptance criterion | 18 August 2026
2 | Add existing issues and pull requests and create two draft planning items. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-02 | Complete | Meets acceptance criterion | 18 August 2026
3 | Create Status, Priority, Iteration and Target date fields. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-03 | Complete | Meets acceptance criterion | 18 August 2026
4 | Configure table, board and roadmap views for different stakeholder questions. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-04 | Complete | Meets acceptance criterion | 18 August 2026
5 | Group or slice one view by owner, status or priority. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-05 | Complete | Meets acceptance criterion | 18 August 2026
6 | Configure a built-in workflow that moves closed items to Done. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-06 | Complete | Meets acceptance criterion | 18 August 2026
7 | Create a milestone and associate the release issues or pull requests. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-07 | Complete | Meets acceptance criterion | 18 August 2026
8 | Create an insight chart and interpret one bottleneck or workload imbalance. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-08 | Complete | Meets acceptance criterion | 18 August 2026
9 | Export the release inventory and observations into the Excel workbook. | Visible GitHub state, command output, or documented decision | Sample evidence recorded | https://github.com/example/evidence/lab-11/step-09 | Complete | Meets acceptance criterion | 18 August 2026

## Acceptance Check
Acceptance Check
The lab is complete only when every criterion is evidenced.
Criterion | Evidence reference | Self-check | Reviewer decision | Gap / next action
Three views answer different questions | Evidence Log step 2 | Met | Accepted
Fields are populated | Evidence Log step 4 | Met | Accepted
Workflow is enabled | Evidence Log step 6 | Met | Accepted
Insight is interpreted | Evidence Log step 8 | Met | Accepted

## Command and Decision Log
Command and Decision Log
Use this sheet for Git commands, GitHub settings and reasoning.
No. | Command / setting | Purpose | Result / output | Decision / interpretation | Evidence ref
1 | Verification | Confirm final state | Passed | Acceptance criterion met | Acceptance Check
2 | Verification | Confirm final state | Passed | Acceptance criterion met | Acceptance Check
3
4
5
6
7
8
9
10
11
12

## Dashboard
Lab Dashboard
Formula-driven completion and evidence summary.
Metric | Value | Target | Status
Steps complete |  | 9
Evidence links |  | 9
Criteria accepted |  | 4
Reviewer notes |  | 9